ATOMICHUB

Complete Product Development Sprint Plan

16 Sprints  •  End-to-End  •  Every Task  •  Every Dependency

| Total Sprints | Total Duration | V1 Ship Sprint | Stack |
| --- | --- | --- | --- |
| 16 sprints | ~32 weeks solo | Sprint 16 | Next.js + Hono + Neon + Redis + Qdrant + R2 |

# Master Sprint Overview

Every sprint is 2 weeks. Working solo, this is a realistic full V1 build plan. Each sprint has a clear deliverable that is independently deployable and demonstrable. Nothing is built before the feature it serves.

| Sprint | Name | Core Output | Unlocks |
| --- | --- | --- | --- |
| S01 | Foundation & Infra | Deployed skeleton: Vercel + Render + Auth + DB | Everything |
| S02 | Component Repo Core | Create, view, delete component repos | S03, S04 |
| S03 | Commit Engine | SHA commits, history, R2 storage | S04, S05, S08 |
| S04 | Branching & PRs | Branches, pull requests, merge strategies | S05, S11 |
| S05 | Tags, Releases, Revert | Semver tags, release notes, revert-via-PR | S13 npm |
| S06 | CLI Tool v1 | atomichub init/login/add/push/commit/log | S10, S14 |
| S07 | Design DNA Engine | Cold start wizard, GitHub analysis, DNA storage | S08, S09, S10 |
| S08 | Prop Playground | Sandpack + controls + Monaco 3-panel editor | S09, S11 |
| S09 | Visual Diffing | Code diff + screenshot diff + prop diff | S04, S08 |
| S10 | Screenshot→Component | AI pipeline, BullMQ, quota, iteration loop | S11, S12 |
| S11 | MCP Server v1 | CF Workers MCP, 10 tools, Redis cache, auth | Sharp edge live |
| S12 | Universal URL Import | URL fetch, dep resolver, DNA adaptation | S13 |
| S13 | npm + Verdaccio | Verdaccio deploy, auto-publish on tag | Distribution |
| S14 | Cross-Project Sync | atomichub.lock, notifications, visual diff, apply | Sync feature |
| S15 | AI Suite Completion | A11y fix, dark mode, responsive, composition, video | AI complete |
| S16 | Social + Polish + Launch | Feed, fork, star, comments, profiles, onboarding | V1 SHIP |

SPRINT 01    Foundation & Infrastructure

| Duration 2 weeks | Goal Get the skeleton deployed end-to-end | Ship Deployed URL with auth working |
| --- | --- | --- |

WHY FIRST You cannot build anything without the deployment pipeline working. Every sprint after this assumes auth, DB, and deployed services exist. Discovering infra problems in Sprint 6 is catastrophic. Discovering them in Sprint 1 is expected.

### Setup Order — Do Exactly This Sequence

- Create GitHub monorepo: atomichub/

- Scaffold Next.js app: apps/web/ (npx create-next-app)

- Scaffold Hono API: apps/api/ (manual, not a framework generator)

- Set up Turborepo workspace: turbo.json, root package.json

- Create packages/: shared TypeScript types, db schema, utils

- Set up Neon PostgreSQL account → get connection string

- Install Drizzle ORM in apps/api/, write drizzle.config.ts

- Write initial schema: users, workspaces tables ONLY

- Run first migration: drizzle-kit push

- Set up Upstash Redis → get REST URL and token

- Set up Clerk → configure OAuth (GitHub + Google)

- Deploy apps/api/ to Render (Docker or Node service)

- Deploy apps/web/ to Vercel (auto-detect Next.js)

- Wire env vars: DATABASE_URL, REDIS_URL, CLERK keys in both services

- Implement Clerk webhook → upsert user into users table on signup

- Build: GET /api/health → returns { status: 'ok', db: 'ok', redis: 'ok' }

- Build: GET /api/me → returns authenticated user from DB

- Build: basic Next.js layout with Clerk SignIn/SignUp components

- Verify: sign up → user row in Neon → /api/me returns user

- Set up Cloudflare R2 bucket: atomichub-components

- Write R2 SDK wrapper in packages/storage/

- Write test: upload file to R2, fetch it back, assert contents match

### Tasks

| ID | Task | Type | Blocker? |
| --- | --- | --- | --- |
| T01-01 | Monorepo scaffold (Turborepo + pnpm workspaces) | Infra | Yes — blocks all |
| T01-02 | Neon PostgreSQL account + initial schema (users, workspaces) | DB | Yes |
| T01-03 | Drizzle ORM setup + first migration | DB | Yes |
| T01-04 | Upstash Redis setup + connection test | Infra | Yes |
| T01-05 | Clerk account + OAuth providers (GitHub + Google) | Auth | Yes |
| T01-06 | Clerk webhook → user upsert in DB | Auth | Yes |
| T01-07 | Hono API scaffold: app.ts, router mounting, error handler middleware | Backend | Yes |
| T01-08 | Auth middleware: Clerk JWT → user_id extraction on every route | Backend | Yes |
| T01-09 | GET /api/health (DB ping + Redis ping) | Backend | No |
| T01-10 | GET /api/me (return authed user from DB) | Backend | No |
| T01-11 | Render deployment (Docker or Node, env vars configured) | Infra | Yes |
| T01-12 | Vercel deployment (Next.js, env vars configured) | Infra | Yes |
| T01-13 | Next.js layout: Clerk provider, nav, auth buttons | Frontend | No |
| T01-14 | Sign-in page using Clerk components | Frontend | No |
| T01-15 | Cloudflare R2 setup + SDK wrapper in packages/storage/ | Storage | No |
| T01-16 | R2 upload/download integration test | Storage | No |
| T01-17 | Environment variable audit: all services have all required vars | Infra | Yes |

SPRINT 01 DONE WHEN You can sign up, see your user in Neon dashboard, hit /api/me and get your profile back, upload a test file to R2 and retrieve it. Render and Vercel are both live at real URLs.

SPRINT 02    Component Repo Core

| Duration 2 weeks | Goal CRUD for component repos + workspace model | Ship Create/view/delete repos in the UI |
| --- | --- | --- |

WHAT WE'RE BUILDING The fundamental entity of AtomicHub. A component repo is a named, versioned container for one component. This sprint builds the data model, API, and UI for managing repos — no git features yet, just create/read/update/delete. Think of this as 'GitHub repo creation page' level functionality.

### DB Schema to Add

-- Add to migration 002 CREATE TABLE workspaces ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), user_id UUID REFERENCES users(id) ON DELETE CASCADE, name TEXT NOT NULL, description TEXT, is_default BOOLEAN DEFAULT false, created_at TIMESTAMPTZ DEFAULT now() ); CREATE TABLE component_repos ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), user_id UUID REFERENCES users(id) ON DELETE CASCADE, workspace_id UUID REFERENCES workspaces(id), name TEXT NOT NULL, slug TEXT NOT NULL, description TEXT, framework TEXT NOT NULL CHECK (framework IN ('react','nextjs','webcomponent')), is_public BOOLEAN DEFAULT true, fork_of_id UUID REFERENCES component_repos(id), star_count INT DEFAULT 0, fork_count INT DEFAULT 0, created_at TIMESTAMPTZ DEFAULT now(), updated_at TIMESTAMPTZ DEFAULT now(), UNIQUE(user_id, slug) ); CREATE INDEX idx_repos_user ON component_repos(user_id); CREATE INDEX idx_repos_public ON component_repos(is_public) WHERE is_public = true;

### API Endpoints to Build

| Method | Route | What it does |
| --- | --- | --- |
| POST | /api/workspaces | Create workspace. Auto-create 'default' workspace on first user signup. |
| GET | /api/workspaces | List all workspaces for authed user |
| GET | /api/workspaces/:id | Get single workspace with component count |
| POST | /api/workspaces/:id/components | Create new component repo in workspace |
| GET | /api/workspaces/:id/components | List all component repos in workspace |
| GET | /api/components/:id | Get single component repo metadata |
| PATCH | /api/components/:id | Update name, description, visibility |
| DELETE | /api/components/:id | Soft delete (set deleted_at, don't destroy data) |

### Frontend Pages to Build

- Dashboard page: /dashboard — shows all workspaces with component counts

- Workspace page: /workspace/:id — grid of component repo cards

- New repo modal: form with name, description, framework selector, visibility toggle

- Component repo page: /c/:username/:slug — empty state (commits come in S03)

- Sidebar navigation: workspaces list, active workspace indicator

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T02-01 | DB migration: workspaces + component_repos tables + indexes | DB | T01-03 |
| T02-02 | Drizzle schema file: workspace + componentRepo models | DB | T02-01 |
| T02-03 | Auto-create default workspace on user signup (Clerk webhook) | Backend | T02-01 |
| T02-04 | POST /api/workspaces — create workspace | Backend | T02-02 |
| T02-05 | GET /api/workspaces — list user workspaces | Backend | T02-02 |
| T02-06 | POST /api/workspaces/:id/components — create repo, validate slug uniqueness | Backend | T02-02 |
| T02-07 | GET /api/workspaces/:id/components — list repos with metadata | Backend | T02-02 |
| T02-08 | GET /api/components/:id — single repo detail | Backend | T02-02 |
| T02-09 | PATCH /api/components/:id — update name/desc/visibility | Backend | T02-02 |
| T02-10 | DELETE /api/components/:id — soft delete with ownership check | Backend | T02-02 |
| T02-11 | React Query hooks: useWorkspaces, useComponents, useMutations | Frontend | T02-04 |
| T02-12 | Dashboard page: workspace list with component counts | Frontend | T02-11 |
| T02-13 | Workspace detail page: component repo grid/list with framework badges | Frontend | T02-11 |
| T02-14 | New repo modal: name + desc + framework + visibility | Frontend | T02-11 |
| T02-15 | Component repo page: header, meta, empty state placeholder | Frontend | T02-08 |
| T02-16 | Sidebar: workspace switcher, new workspace button | Frontend | T02-11 |
| T02-17 | URL routing: /dashboard, /w/:workspaceId, /c/:username/:slug | Frontend | None |
| T02-18 | Error states: 404 for missing repos, 403 for private repos | Frontend | T02-08 |

SPRINT 02 DONE WHEN You can create a workspace, create a component repo inside it, view it on a page, edit its description, and delete it. The repo page exists but has no code/commits yet.

SPRINT 03    Commit Engine

| Duration 2 weeks | Goal SHA commits + R2 source storage + history view | Ship Push code and see commit history |
| --- | --- | --- |

THE CORE This is the heart of AtomicHub. The commit engine is what makes it a version control system rather than a file hosting service. Every component interaction — AI generation, URL import, fork adaptation, CLI push — ultimately creates a commit. Get this right.

### DB Schema to Add

CREATE TABLE branches ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), repo_id UUID REFERENCES component_repos(id) ON DELETE CASCADE, name TEXT NOT NULL, head_commit_sha TEXT, is_protected BOOLEAN DEFAULT false, created_at TIMESTAMPTZ DEFAULT now(), UNIQUE(repo_id, name) ); CREATE TABLE commits ( sha TEXT PRIMARY KEY, repo_id UUID REFERENCES component_repos(id) ON DELETE CASCADE, branch_id UUID REFERENCES branches(id), parent_sha TEXT REFERENCES commits(sha), author_id UUID REFERENCES users(id), message TEXT NOT NULL, source_key TEXT NOT NULL, -- R2 object key metadata_key TEXT, -- R2 key for atomichub.json ai_assisted BOOLEAN DEFAULT false, ai_model TEXT, coherence_score INT, human_ratio NUMERIC(4,2), created_at TIMESTAMPTZ DEFAULT now() ); CREATE INDEX idx_commits_repo ON commits(repo_id, created_at DESC); CREATE INDEX idx_commits_branch ON commits(branch_id, created_at DESC);

### Commit SHA Algorithm

// packages/vcs/src/sha.ts import { createHash } from 'crypto'; export function computeCommitSHA(input: { source: string; parentSHA: string ¦ null; authorId: string; repoId: string; timestamp: string; message: string; }): string { const content = JSON.stringify(input); return createHash('sha256').update(content).digest('hex'); } // Two commits with same source but different parents → different SHA // Same content committed twice → different SHA (timestamp differs) // This matches git's approach: history matters, not just content

### API Endpoints to Build

| Method | Route | What it does |
| --- | --- | --- |
| POST | /api/components/:id/commits | Create commit: accept source code, compute SHA, upload to R2, update branch HEAD |
| GET | /api/components/:id/commits | List commit history for default branch (paginated) |
| GET | /api/components/:id/commits/:sha | Get single commit metadata |
| GET | /api/components/:id/source | Get current source (latest commit on default branch) |
| GET | /api/components/:id/source/:sha | Get source at specific commit SHA |

### R2 Storage Pattern

// Source file path pattern: // atomichub-components/{user_id}/{repo_id}/{commit_sha}/component.tsx // On commit creation: async function createCommit(input: CommitInput): Promise<Commit> { const sha = computeCommitSHA({ ...input, timestamp: new Date().toISOString() }); // 1. Upload source to R2 const key = `${input.userId}/${input.repoId}/${sha}/component.tsx`; await r2.put(key, input.source); // 2. Insert commit row const commit = await db.insert(commits).values({ sha, source_key: key, branch_id: input.branchId, parent_sha: input.parentSha, message: input.message, author_id: input.authorId, repo_id: input.repoId, }).returning(); // 3. Update branch HEAD await db.update(branches) .set({ head_commit_sha: sha }) .where(eq(branches.id, input.branchId)); return commit; }

### Frontend to Build

- Component repo page: source code viewer (Monaco, read-only) showing latest commit

- Commit history timeline: list of commits with SHA, message, author, timestamp

- Commit detail page: /c/:username/:slug/commit/:sha — shows source at that commit

- 'Make first commit' UI: paste source code → commit message → submit

- Commit message validation: enforce Conventional Commits format (feat:, fix:, etc.)

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T03-01 | DB migration: branches + commits tables | DB | T02-01 |
| T03-02 | Auto-create 'main' branch on component repo creation | Backend | T03-01 |
| T03-03 | computeCommitSHA() utility in packages/vcs/ | Backend | None |
| T03-04 | R2 upload helper: put source, return object key | Backend | T01-15 |
| T03-05 | POST /api/components/:id/commits — full commit creation flow | Backend | T03-03, T03-04 |
| T03-06 | GET /api/components/:id/commits — paginated history | Backend | T03-01 |
| T03-07 | GET /api/components/:id/source — fetch current source from R2 via presigned URL | Backend | T03-05 |
| T03-08 | GET /api/components/:id/source/:sha — fetch source at specific commit | Backend | T03-05 |
| T03-09 | Presigned URL generation: time-limited R2 read URLs (15 min TTL) | Backend | T01-15 |
| T03-10 | Monaco editor component (read-only) with syntax highlighting | Frontend | None |
| T03-11 | Commit history timeline component | Frontend | T03-06 |
| T03-12 | Component repo page: source viewer + commit history tab | Frontend | T03-10, T03-11 |
| T03-13 | 'New commit' flow: code editor + message input + submit | Frontend | T03-05 |
| T03-14 | Commit detail page: source at SHA + commit metadata | Frontend | T03-08 |
| T03-15 | Conventional commit message validator (client-side) | Frontend | None |
| T03-16 | Redis cache: repo:source:{repo_id} → latest source presigned URL (5 min TTL) | Backend | T03-07 |

SPRINT 03 DONE WHEN You can paste component code into the UI, commit it with a message, see it in the history, click any commit and see the exact source at that point in time. The SHA is computed correctly and stored in R2.

SPRINT 04    Branching & Pull Requests

| Duration 2 weeks | Goal Full git branching + PR workflow | Ship Create branch, open PR, merge it |
| --- | --- | --- |

### API Endpoints

| Method | Route | What it does |
| --- | --- | --- |
| POST | /api/components/:id/branches | Create branch from any commit SHA or branch name |
| GET | /api/components/:id/branches | List all branches with HEAD commit info |
| DELETE | /api/components/:id/branches/:name | Delete branch (not if protected, not if main) |
| POST | /api/components/:id/prs | Open PR: source branch → target branch |
| GET | /api/components/:id/prs | List PRs (open/merged/closed) with status |
| GET | /api/components/:id/prs/:prId | Get PR detail with diff data |
| POST | /api/components/:id/prs/:prId/merge | Merge PR (merge/squash/rebase strategy) |
| POST | /api/components/:id/prs/:prId/close | Close PR without merging |
| POST | /api/components/:id/prs/:prId/comments | Add inline comment to PR |
| GET | /api/components/:id/prs/:prId/comments | List PR comments |

### PR Merge Logic

// Three merge strategies: // 1. Merge commit: preserves branch history // Creates a new commit with 2 parents (like git merge) // 2. Squash: collapses all branch commits into one // Single commit on target with message = PR title // 3. Rebase: replays branch commits on top of target // Linear history, each commit re-SHA'd with new parent // All strategies: update target branch HEAD after merge // All strategies: create pr_merge_event row for audit // Protected branch (main): require PR, block direct commits

### PR Automated Checks

// On PR creation, enqueue background checks: // 1. No merge conflicts (diff source HEAD vs target HEAD) // 2. Coherence score delta (will score go up or down?) // 3. Contract compliance (does source branch pass active contracts?) // Results stored on pull_requests.checks_passed // Shown as status badges in PR UI

### Frontend Pages

- Branch selector dropdown on component repo page (replaces 'main' hardcode)

- Branch list page: /c/:username/:slug/branches — all branches, create button

- PR list page: /c/:username/:slug/pulls — open/merged/closed tabs

- PR detail page: code diff view, comments, checks status, merge button

- Inline commenting: click any diff line to add comment

- Merge strategy selector in PR merge dialog

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T04-01 | DB migration: pull_requests, pr_comments tables | DB | T03-01 |
| T04-02 | POST /api/components/:id/branches — create from SHA or branch | Backend | T03-05 |
| T04-03 | GET /api/components/:id/branches — list with HEAD info | Backend | T04-02 |
| T04-04 | Branch protection: block direct commits to main | Backend | T04-02 |
| T04-05 | POST /api/components/:id/prs — create PR with conflict check | Backend | T04-02 |
| T04-06 | GET /api/components/:id/prs — list with status | Backend | T04-05 |
| T04-07 | GET /api/components/:id/prs/:prId — detail with diff | Backend | T04-05 |
| T04-08 | Merge commit strategy implementation | Backend | T04-05 |
| T04-09 | Squash merge strategy implementation | Backend | T04-05 |
| T04-10 | Rebase merge strategy implementation | Backend | T04-05 |
| T04-11 | POST /api/components/:id/prs/:prId/comments — inline comment | Backend | T04-05 |
| T04-12 | PR automated checks: conflict detection + coherence delta | Backend | T04-05 |
| T04-13 | Branch selector UI component (dropdown with branch list) | Frontend | T04-03 |
| T04-14 | Branch list page | Frontend | T04-03 |
| T04-15 | Open PR form: source branch, target branch, title, description | Frontend | T04-05 |
| T04-16 | PR list page with status tabs | Frontend | T04-06 |
| T04-17 | PR detail: unified diff view with syntax highlighting | Frontend | T04-07 |
| T04-18 | Inline comment UI on diff lines | Frontend | T04-11 |
| T04-19 | Merge dialog: strategy selector + confirm | Frontend | T04-08 |
| T04-20 | PR checks status badges (conflict, coherence delta, contracts) | Frontend | T04-12 |

SPRINT 04 DONE WHEN You can create a branch, make a commit on it, open a PR against main, see the diff, add a comment, and merge it. Main branch HEAD updates correctly after merge.

SPRINT 05    Tags, Releases & Revert

| Duration 2 weeks | Goal Semver versioning + release notes + revert-via-PR | Ship Tag a release, revert a component |
| --- | --- | --- |

### DB Schema to Add

CREATE TABLE version_tags ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), repo_id UUID REFERENCES component_repos(id) ON DELETE CASCADE, tag TEXT NOT NULL, -- '1.0.0', '1.2.0-beta.1' commit_sha TEXT REFERENCES commits(sha), channel TEXT DEFAULT 'stable', -- stable ¦ beta ¦ canary release_notes TEXT, npm_published BOOLEAN DEFAULT false, created_at TIMESTAMPTZ DEFAULT now(), UNIQUE(repo_id, tag) );

### API Endpoints

| Method | Route | What it does |
| --- | --- | --- |
| POST | /api/components/:id/tags | Create semver tag at a commit SHA. Validate semver format. Auto-generate release notes from commits since last tag. |
| GET | /api/components/:id/tags | List all version tags newest first |
| GET | /api/components/:id/tags/:tag | Get tag detail + source at that version |
| POST | /api/components/:id/revert | Create a revert PR: compute inverse diff, open PR against main, title 'revert: revert to v{tag}' |

### Release Notes Auto-Generation

// When tagging v1.2.0, find all commits since v1.1.0 // Group by conventional commit prefix: // ## What's New // - feat: add loading state to Button // - feat: support icon prop // ## Bug Fixes // - fix: focus ring not visible in Windows high contrast // ## Maintenance // - chore: update Tailwind config // Stored in version_tags.release_notes as markdown

### Revert Implementation

// Revert creates a PR, not a force-push // This preserves history (same as GitHub's revert button) // Steps: // 1. Fetch source at target version (the one to revert TO) // 2. Fetch source at current HEAD // 3. Create revert branch: revert/to-v{targetVersion} // 4. Commit the target source onto revert branch // Message: 'revert: revert to v{targetVersion}' // 5. Open PR: revert branch → main // 6. Return PR URL to user

### Frontend Pages

- Releases page: /c/:username/:slug/releases — list of tags with release notes

- Tag creation dialog: semver input, channel selector, release notes editor

- Release detail page: full release notes + source viewer at that version

- Revert button on any tag/commit: triggers revert PR creation, links to PR

- Version badge on component repo page: shows latest stable version

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T05-01 | DB migration: version_tags table | DB | T03-01 |
| T05-02 | POST /api/components/:id/tags — validate semver, create tag | Backend | T05-01 |
| T05-03 | Auto-generate release notes from commit history since last tag | Backend | T05-02 |
| T05-04 | GET /api/components/:id/tags — list releases | Backend | T05-01 |
| T05-05 | GET /api/components/:id/tags/:tag — detail + source | Backend | T05-04 |
| T05-06 | POST /api/components/:id/revert — revert-via-PR flow | Backend | T04-05, T05-05 |
| T05-07 | Releases page UI | Frontend | T05-04 |
| T05-08 | Tag creation dialog with semver validation | Frontend | T05-02 |
| T05-09 | Release detail page | Frontend | T05-05 |
| T05-10 | Revert button + confirmation dialog | Frontend | T05-06 |
| T05-11 | Latest version badge on repo page | Frontend | T05-04 |
| T05-12 | Version selector in source view (switch between versions) | Frontend | T05-05 |

SPRINT 05 DONE WHEN You can tag v1.0.0, see auto-generated release notes, view source at that version, and click Revert to get a PR that restores that version's code.

SPRINT 06    CLI Tool v1

| Duration 2 weeks | Goal Full atomichub CLI: init, login, add, push, commit, log | Ship Developer works entirely from terminal |
| --- | --- | --- |

WHY CLI BEFORE DNA The CLI is the developer interface to the VCS engine. It needs to exist before we build features that generate commits (DNA import, URL import, AI generation) — those all use the same commit API the CLI exercises. Building CLI now validates the API contract before adding complexity.

### CLI Architecture

packages/cli/ src/ commands/ init.ts # atomichub init login.ts # atomichub login (browser OAuth flow) logout.ts # atomichub logout add.ts # atomichub add <component> push.ts # atomichub push <component> commit.ts # atomichub commit -m 'message' log.ts # atomichub log status.ts # atomichub status diff.ts # atomichub diff <v1> <v2> branch.ts # atomichub branch <name> checkout.ts # atomichub checkout <branch/tag> sync.ts # atomichub sync import.ts # atomichub import <url> config.ts # ~/.atomichub/config.json read/write api.ts # typed API client (wraps fetch) lock.ts # atomichub.lock read/write bin/atomichub.ts # entry point package.json # { bin: { atomichub: './bin/atomichub.js' } }

### Login Flow

atomichub login 1. Generate random state + code_verifier (PKCE) 2. Build Clerk OAuth URL with state + code_challenge 3. Open browser: open('https://atomichub.dev/cli-auth?state={state}') 4. Web app: user sees 'Authorize AtomicHub CLI' button 5. On authorize: exchange code for token via PKCE 6. Web app calls: POST /api/auth/cli-token { code, code_verifier } 7. Server returns scoped API token 8. CLI polls: GET /api/auth/cli-pending?state={state} every 2s 9. On token available: save to ~/.atomichub/config.json 10. Print: '✓ Logged in as @username'

### atomichub add Command

atomichub add Button 1. Read atomichub.lock — check if Button already added 2. GET /api/components?name=Button&workspace={activeWorkspace} → { repo_id, latest_tag, framework } 3. GET /api/components/:id/source (presigned R2 URL returned) 4. Fetch source from presigned URL 5. Read project package.json 6. GET /api/components/:id/tags/latest → dep_manifest 7. Compute missing deps: dep_manifest.peerDeps - existing package.json.deps 8. If missing deps: prompt 'Install X missing deps? (Y/n)' 9. Run: npm install {missing_deps} 10. Write source to ./components/Button/component.tsx 11. Update atomichub.lock: { Button: { repo_id, tag, added_at } } 12. POST /api/sync/register-usage { project_id, repo_id, tag } 13. Print: '✓ Added Button@1.2.0 → components/Button/'

### Config File Schema

// ~/.atomichub/config.json { "token": "ah_tok_...", "username": "allwin23", "activeWorkspace": "uuid-here", "apiUrl": "https://api.atomichub.dev" } // ./atomichub.lock (project root, commit this to git) { "Button": { "repo_id": "uuid", "tag": "1.2.0", "workspace_id": "uuid" }, "Card": { "repo_id": "uuid", "tag": "0.8.1", "workspace_id": "uuid" } }

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T06-01 | packages/cli/ scaffold: bin entry, tsup build, npm link for local dev | CLI | None |
| T06-02 | config.ts: read/write ~/.atomichub/config.json | CLI | T06-01 |
| T06-03 | api.ts: typed fetch wrapper with Authorization header injection | CLI | T06-02 |
| T06-04 | lock.ts: atomichub.lock read/write/update | CLI | T06-01 |
| T06-05 | login command: PKCE browser flow + polling | CLI | T06-03 |
| T06-06 | API: POST /api/auth/cli-token + GET /api/auth/cli-pending | Backend | T01-08 |
| T06-07 | init command: create atomichub.lock, prompt for workspace | CLI | T06-04 |
| T06-08 | add command: fetch + dep resolve + write + lock update + register | CLI | T06-03, T06-04 |
| T06-09 | push command: read local source + POST /api/components/:id/commits | CLI | T06-03 |
| T06-10 | commit command: stage + message + push in one step | CLI | T06-09 |
| T06-11 | log command: GET commits, pretty-print history | CLI | T06-03 |
| T06-12 | status command: show local vs remote HEAD diff | CLI | T06-03 |
| T06-13 | branch command: create + list branches | CLI | T06-03 |
| T06-14 | checkout command: switch branch or version tag | CLI | T06-03 |
| T06-15 | sync command: apply pending sync notifications (placeholder — full in S14) | CLI | T06-04 |
| T06-16 | Error handling: 401 (token expired), 404 (component not found), network errors | CLI | T06-03 |
| T06-17 | CLI output: chalk colors, spinner (ora), consistent format | CLI | T06-01 |
| T06-18 | Publish CLI to npm as atomichub-cli | CLI | T06-01 |

SPRINT 06 DONE WHEN You can run atomichub login, atomichub init in a project, atomichub add Button, and see the component source appear in your project. atomichub push sends local changes back to AtomicHub.

SPRINT 07    Design DNA Engine

| Duration 2 weeks | Goal Cold start wizard + GitHub analysis + DNA storage + topology | Ship DNA profile populated and visible |
| --- | --- | --- |

### DB Schema to Add

CREATE TABLE global_dna ( user_id UUID PRIMARY KEY REFERENCES users(id) ON DELETE CASCADE, spacing_scale JSONB, color_system JSONB, typography JSONB, border_system JSONB, animation JSONB, naming JSONB, framework_conventions JSONB, cold_start_complete BOOLEAN DEFAULT false, source TEXT, -- 'wizard' ¦ 'github' ¦ 'upload' ¦ 'progressive' confidence INT DEFAULT 0, -- 0-100 updated_at TIMESTAMPTZ DEFAULT now() ); CREATE TABLE workspace_dna ( workspace_id UUID PRIMARY KEY REFERENCES workspaces(id) ON DELETE CASCADE, overrides JSONB NOT NULL DEFAULT '{}', dark_mode TEXT DEFAULT 'optional', contracts TEXT[] DEFAULT '{}', updated_at TIMESTAMPTZ DEFAULT now() ); CREATE TABLE topology_reports ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), user_id UUID REFERENCES users(id) ON DELETE CASCADE, workspace_id UUID REFERENCES workspaces(id), consistency_score INT, token_coverage INT, a11y_baseline INT, dark_mode_coverage INT, suggestions JSONB, created_at TIMESTAMPTZ DEFAULT now() );

### Cold Start Wizard — 5 Questions

| Q | Question | Options | Maps to DNA field |
| --- | --- | --- | --- |
| Q1 | How tight is your spacing? | A) Dense (4px) B) Comfortable (8px) C) Airy (12px) | spacing_scale.base |
| Q2 | Pick your border radius style | A) Sharp (0) B) Subtle (4px) C) Rounded (8px) D) Pill | border_system.radius_preset |
| Q3 | How do you prefer animations? | A) None B) Subtle+functional C) Expressive+playful | animation.personality |
| Q4 | Upload brand colors | Primary + secondary color pickers | color_system.primary/secondary |
| Q5 | Pick your typography stack | 6 font pair previews to choose from | typography.heading/body_font |

### GitHub Analysis Pipeline

// BullMQ job: dna:analysis async function analyzeGitHubRepos(userId: string, githubToken: string) { // 1. List repos via GitHub API const repos = await github.listRepos(githubToken, { language: 'TypeScript' }); // 2. For each repo, fetch all .tsx/.jsx files const sourceFiles = await github.fetchSourceFiles(repos.slice(0, 5)); // cap at 5 repos // 3. AST analysis via TypeScript compiler API: // - Extract all Tailwind className values → spacing patterns, colors // - Extract CSS variable names → token naming conventions // - Extract prop interface names → naming style (camelCase vs PascalCase) // - Extract animation/transition usages → motion personality // - Count border-radius values → radius preference // 4. Aggregate patterns, pick dominant values // 5. Optional LLM summary pass (Claude haiku — cheap): // 'Given these patterns, describe this developer's design style in 3 sentences' // 6. Upsert global_dna: source='github', confidence=75 }

### Workspace DNA Wizard

- Step 1: Project name + description

- Step 2: Brand colors (primary, secondary, semantic: success/error/warning)

- Step 3: Typography (heading font, body font — from Google Fonts picker)

- Step 4: Spacing base unit, dark mode requirement (required/optional/none)

- Step 5: Active design contracts (multi-select from built-in contract list)

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T07-01 | DB migration: global_dna, workspace_dna, topology_reports | DB | T02-01 |
| T07-02 | Cold start wizard UI: 5-step form with visual options | Frontend | None |
| T07-03 | POST /api/dna/cold-start — save wizard answers as DNA JSON | Backend | T07-01 |
| T07-04 | GitHub OAuth scope: add repo read scope to Clerk OAuth config | Auth | T01-05 |
| T07-05 | GET /api/auth/github-token — exchange Clerk session for GitHub token | Backend | T01-08 |
| T07-06 | BullMQ job: dna:analysis — GitHub repo fetch + AST analysis pipeline | Backend | T07-01 |
| T07-07 | TypeScript compiler API (ts-morph) integration for AST parsing | Backend | None |
| T07-08 | Pattern aggregator: extract dominant spacing, colors, naming from AST | Backend | T07-07 |
| T07-09 | POST /api/dna/analyze-github — trigger dna:analysis job | Backend | T07-06 |
| T07-10 | GET /api/dna — return user's global DNA (with Redis caching) | Backend | T07-01 |
| T07-11 | PATCH /api/dna — manual update any DNA field | Backend | T07-01 |
| T07-12 | Workspace DNA wizard UI (5 steps) | Frontend | None |
| T07-13 | POST /api/workspaces/:id/dna — save workspace DNA overrides | Backend | T07-01 |
| T07-14 | GET /api/workspaces/:id/dna/effective — merge global + workspace DNA | Backend | T07-10 |
| T07-15 | Redis cache: dna:effective:{uid}:{wid} (30 min TTL) | Backend | T07-14 |
| T07-16 | DNA profile UI page: visual display of all DNA fields with edit controls | Frontend | T07-10 |
| T07-17 | Topology report job: dna:topology — analyze library consistency | Backend | T07-01 |
| T07-18 | Topology report UI: scores + suggestions display | Frontend | T07-17 |
| T07-19 | BullMQ queue setup: dna:analysis + dna:topology queues | Backend | None |

SPRINT 07 DONE WHEN A new user can complete the 5-question wizard OR connect GitHub and have DNA auto-populated. DNA is visible on a profile page. Workspace DNA can be configured per workspace with its own brand colors and typography.

SPRINT 08    Prop Playground

| Duration 2 weeks | Goal 3-panel: controls + sandpack live preview + Monaco editor | Ship Interactive component exploration |
| --- | --- | --- |

### Architecture

// Three panels in ComponentPlayground.tsx // Panel 1: Controls (left) // - Auto-generated from component.props.json // - string → TextInput, boolean → Toggle // - enum → Select, number → Slider, ReactNode → slot indicator // Panel 2: Live Preview (center) // - Sandpack in-browser bundler // - Files: component.tsx (from R2) + App.tsx (generated from prop state) // - Hot reload on every prop change // - Viewport selector: mobile/tablet/desktop/wide // - Light/dark mode toggle // Panel 3: Code Editor (right) // - Monaco editor (editable) // - Shows App.tsx with current prop values applied // - Manual edits reflect in preview instantly // - 'Save as variant' button

### Prop Schema Generation

// packages/vcs/src/propSchema.ts // Runs as part of every commit + publish import { Project } from 'ts-morph'; function extractProps(source: string): PropSchema[] { const project = new Project({ useInMemoryFileSystem: true }); const file = project.createSourceFile('component.tsx', source); // Find Props interface or type alias const propsType = file.getInterface('Props') ¦¦ file.getTypeAlias('Props'); if (!propsType) return []; return propsType.getProperties().map(prop => ({ name: prop.getName(), type: prop.getType().getText(), required: !prop.hasQuestionToken(), default: extractDefaultFromJSDoc(prop), controlType: inferControl(prop.getType()), enumValues: extractUnion(prop.getType()), })); } function inferControl(type: Type): ControlType { if (type.isBoolean()) return 'toggle'; if (type.isString()) return 'text'; if (type.isNumber()) return 'number'; if (type.isUnion()) return 'select'; return 'unsupported'; }

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T08-01 | Prop schema extraction (ts-morph) run on every commit | Backend | T03-05 |
| T08-02 | Store component.props.json to R2 alongside source on commit | Backend | T08-01 |
| T08-03 | GET /api/components/:id/props — return prop schema JSON | Backend | T08-02 |
| T08-04 | Redis cache: repo:props:{id}:{sha} (24hr TTL — immutable per commit) | Backend | T08-03 |
| T08-05 | Install @codesandbox/sandpack-react in apps/web/ | Frontend | None |
| T08-06 | Controls panel: render correct input per prop controlType | Frontend | T08-03 |
| T08-07 | generateAppWrapper(propValues) — builds App.tsx string from prop state | Frontend | T08-06 |
| T08-08 | Sandpack integration: inject component.tsx + App.tsx, hot reload on change | Frontend | T08-05, T08-07 |
| T08-09 | Viewport selector (mobile/tablet/desktop/wide) with responsive iframe sizes | Frontend | T08-08 |
| T08-10 | Light/dark mode toggle — inject class on sandpack preview root | Frontend | T08-08 |
| T08-11 | Monaco editor (editable) — shows App.tsx, syncs changes to preview | Frontend | T08-08 |
| T08-12 | 3-panel layout: resizable panels (react-resizable-panels) | Frontend | T08-06 |
| T08-13 | 'Fork from state' button: pre-fill fork with current prop defaults | Frontend | T08-08 |
| T08-14 | 'Share state' button: encode prop state in URL query params | Frontend | T08-08 |
| T08-15 | 'Generate story' button: export current state as Storybook story | Frontend | T08-08 |
| T08-16 | Playground loading state: skeleton while sandpack initialises | Frontend | T08-08 |
| T08-17 | Playground route: /c/:username/:slug/playground | Frontend | T08-08 |

SPRINT 08 DONE WHEN Open any component in the Playground, toggle its props with controls, see the component update live, edit the code in Monaco and watch the preview update, change viewport sizes.

SPRINT 09    Visual Diffing

| Duration 2 weeks | Goal Code diff + screenshot diff + prop diff + score delta | Ship See exactly what changed between any two versions |
| --- | --- | --- |

### Four Diff Types

| Diff Type | How Computed | Library |
| --- | --- | --- |
| Code diff | Unified diff algorithm on raw source text | diff (npm), same algo as git |
| Prop diff | Parse TypeScript interfaces from both versions via ts-morph, compare | ts-morph (existing) |
| Screenshot diff | Render both versions headless via Playwright, pixelmatch comparison | Playwright + pixelmatch |
| Score delta | coherence_score + a11y_score + human_ratio from commits table | PostgreSQL query |

### Playwright Screenshot Capture

// Runs in Render service (NOT CF Worker — needs full browser) // Triggered by: visual diff request, PR creation import { chromium } from 'playwright'; async function captureComponentScreenshot(source: string): Promise<Buffer> { const browser = await chromium.launch(); const page = await browser.newPage(); // Inject component via data URI with Sandpack SSR await page.setContent(buildHTMLWrapper(source)); await page.waitForSelector('[data-testid=component-root]'); await page.waitForLoadState('networkidle'); const screenshot = await page.screenshot({ fullPage: false }); await browser.close(); return screenshot; } // pixelmatch comparison: const diff = pixelmatch(img1, img2, diffImg, width, height, { threshold: 0.1 }); const diffPercent = (diff / (width * height)) * 100;

### API Endpoints

| Method | Route | Returns |
| --- | --- | --- |
| GET | /api/components/:id/diff?from=&to= | All 4 diff types: code, props, screenshot URLs, score delta |
| GET | /api/components/:id/prs/:prId/diff | PR diff (source branch HEAD vs target branch HEAD) |

### Diff UI — Draggable Divider

// Visual diff panel: two rendered components side by side // Draggable center divider (like Figma's version history) // Mode toggle: // [Side-by-side] [Overlay] [Diff only] // Side-by-side: Old ¦ NEW with diff percentage badge // Overlay: pixel diff image shown with red = changed pixels // Diff only: only the code diff (unified format, syntax highlighted)

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T09-01 | Code diff engine: unified diff algorithm on two source strings | Backend | None |
| T09-02 | Prop diff engine: ts-morph parse both interfaces, compute delta | Backend | T08-01 |
| T09-03 | Playwright install in Render service Dockerfile | Infra | None |
| T09-04 | captureComponentScreenshot(): Playwright headless render | Backend | T09-03 |
| T09-05 | pixelmatch integration: compare two screenshots, return diff% | Backend | T09-04 |
| T09-06 | Screenshot diff caching: store diff images in R2 (keyed by sha_pair) | Backend | T09-05 |
| T09-07 | GET /api/components/:id/diff — orchestrate all 4 diff types | Backend | T09-01..T09-05 |
| T09-08 | Score delta query from commits table | Backend | T03-01 |
| T09-09 | Diff UI: version selector (from/to dropdowns) | Frontend | T05-04 |
| T09-10 | Code diff viewer: unified diff with syntax highlighting + line numbers | Frontend | T09-07 |
| T09-11 | Prop diff viewer: added/removed/changed props in table | Frontend | T09-07 |
| T09-12 | Screenshot diff: side-by-side + draggable divider + overlay mode | Frontend | T09-07 |
| T09-13 | Score delta display: before/after coherence + a11y + human_ratio | Frontend | T09-08 |
| T09-14 | Wire diff into PR detail page (auto-compute from PR source/target) | Frontend | T09-07 |
| T09-15 | Diff route: /c/:username/:slug/diff?from=:sha&to=:sha | Frontend | T09-09 |

SPRINT 09 DONE WHEN Select any two versions of a component, see all four diff types side by side. Drag the divider in screenshot diff mode. PR detail page shows the visual diff automatically.

SPRINT 10    Screenshot → Component AI

| Duration 2 weeks | Goal Full AI generation pipeline with DNA context + iteration | Ship Upload screenshot, get production component |
| --- | --- | --- |

BEFORE STARTING You need BullMQ worker service deployed on Render before this sprint. The AI pipeline is async — it MUST run in a worker, not the API request handler. Worker deployment should be done in the first 2 days of this sprint.

### BullMQ Worker Setup

apps/worker/ src/ processors/ ai.screenshot.ts ai.coherence.ts dna.analysis.ts # move here from api dna.topology.ts queues.ts # queue definitions + Bull Board (monitoring UI) index.ts # worker entry point // Deploy as separate Render service // Shares same DATABASE_URL and REDIS_URL as API // Does NOT expose HTTP — purely queue consumer

### AI Generation Pipeline

// POST /api/ai/screenshot // 1. Quota check (Redis: quota:{uid}:screenshot) // 2. Upload image to R2: atomichub-ai/jobs/{job_id}/input.png // 3. Insert ai_jobs row: status='queued' // 4. Enqueue BullMQ job: ai:generation // 5. Return 202: { job_id } // Worker processor: ai.screenshot.ts // 1. Fetch effective DNA (Redis → PostgreSQL fallback) // 2. Fetch workspace contracts // 3. Fetch existing component list from user's library (for composition context) // 4. Build system prompt: DNA context + contracts + existing components + target framework // 5. Fetch input image from R2 // 6. Call Claude claude-sonnet-4 vision API (user's Anthropic key) // 7. Parse response → extract TSX component // 8. Run coherence check (Claude haiku, separate call) // 9. Store output.tsx to R2 // 10. Update ai_jobs: status='done', coherence_score, output_ref // 11. INCR Redis quota:{uid}:screenshot // 12. Emit WebSocket event to frontend: job complete

### System Prompt Construction

function buildScreenshotPrompt(dna: EffectiveDNA, contracts: string[], existingComponents: string[]): string { return ` You are an expert React/TypeScript developer. Generate a production-ready component from this screenshot. DESIGN SYSTEM (follow exactly — do not deviate): - Spacing: ${dna.spacing_scale.base}px base unit, scale: ${dna.spacing_scale.scale.join(', ')}px - Primary color: ${dna.color_system.primary} (use CSS variable: var(--color-primary)) - Border radius: ${dna.border_system.radius_preset} - Typography: ${dna.typography.body_font} body, ${dna.typography.heading_font} headings - Animation: ${dna.animation.personality}, easing: ${dna.animation.easing} - Naming: ${dna.naming.props} for props, ${dna.naming.files} for files ACTIVE CONTRACTS (mandatory requirements): ${contracts.map(c => '- ' + c).join('\n')} EXISTING COMPONENTS (use these when possible, don't recreate): ${existingComponents.join(', ')} OUTPUT: TypeScript React component using Tailwind CSS only. No inline styles. Include: loading state, error state, empty state, dark mode support. Export a typed Props interface. Use semantic HTML. Include ARIA attributes.` }

### Iteration Loop UI

- After generation: show result in 3-panel view (Playground mode)

- Iteration input: 'Make it more minimal' / 'Add a hover animation' / 'Use my primary color'

- Each iteration: re-call API with previous output + iteration prompt

- Show diff between iterations (code diff, no screenshot diff — too slow for iteration)

- 'Approve & Commit' button: create commit in repo with AI metadata

- 'Start over' button: discard, go back to upload

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T10-01 | Deploy BullMQ worker as separate Render service | Infra | S06 complete |
| T10-02 | Bull Board monitoring UI (password protected) on worker service | Infra | T10-01 |
| T10-03 | DB migration: ai_jobs table + usage_quotas table | DB | T01-03 |
| T10-04 | Quota check middleware: checkQuota(userId, type) function | Backend | T10-03 |
| T10-05 | POST /api/ai/screenshot — validate, upload input, enqueue, return 202 | Backend | T10-03, T10-04 |
| T10-06 | GET /api/ai/jobs/:id — poll job status + result | Backend | T10-03 |
| T10-07 | User API key storage: encrypt at rest (AES-256-GCM), store in user profile | Backend | T01-08 |
| T10-08 | PATCH /api/user/ai-keys — store Anthropic/OpenAI/Google keys | Backend | T10-07 |
| T10-09 | Worker: ai.screenshot processor — full pipeline with DNA injection | Worker | T10-01, T07-14 |
| T10-10 | buildScreenshotPrompt() — DNA context + contracts + composition context | Worker | T07-14 |
| T10-11 | Coherence check in worker: Claude haiku call, return score + violations | Worker | T10-09 |
| T10-12 | WebSocket setup: socket.io on API, emit 'job:complete' event | Backend | T10-05 |
| T10-13 | Screenshot upload UI: drag-and-drop + file picker + URL input | Frontend | None |
| T10-14 | Job polling / WebSocket listener: show progress spinner during generation | Frontend | T10-06 |
| T10-15 | Result display: component in 3-panel Playground with coherence score | Frontend | T08-08 |
| T10-16 | Iteration input: prompt bar below result, submit → re-generate | Frontend | T10-05 |
| T10-17 | 'Approve & Commit' flow: message input → POST /api/components/:id/commits | Frontend | T10-15 |
| T10-18 | AI keys settings page: add Anthropic / OpenAI / Google keys | Frontend | T10-08 |
| T10-19 | Quota display: show remaining uses per AI feature type | Frontend | T10-06 |

SPRINT 10 DONE WHEN Upload a screenshot of any website's UI element, see AtomicHub generate a React + Tailwind component matching your DNA, iterate on it with follow-up prompts, and commit it to your library.

SPRINT 11    MCP Server

| Duration 2 weeks | Goal Cloudflare Workers MCP + 10 tools + Redis cache + token auth | Ship Claude Code can access your component library |
| --- | --- | --- |

THE SHARP EDGE This is the feature that makes AtomicHub genuinely different from everything else. When this sprint is done, a developer can give an API token to Claude Code and their AI agent will know their entire component history. Demo this immediately after shipping.

### CF Workers Project Structure

apps/mcp/ src/ index.ts # Worker entry point, route handler auth.ts # Token validation via Redis + internal API tools/ search.ts # atomichub.search get.ts # atomichub.get getDNA.ts # atomichub.getDNA list.ts # atomichub.listWorkspace push.ts # atomichub.push checkCoherence.ts diff.ts getContracts.ts suggestComposition.ts context.ts # Inject DNA context into every response cache.ts # Upstash Redis operations wrangler.toml # CF Workers config

### MCP Protocol Implementation

// MCP uses JSON-RPC 2.0 over HTTP (SSE for streaming) // AtomicHub implements: tools/list + tools/call // POST /mcp // Body: { jsonrpc: '2.0', id: 1, method: 'tools/call', // params: { name: 'atomichub.search', arguments: { query: '...' } } } // Every response includes dna_context in metadata: // { result: {...}, _meta: { dna_context: {...}, existing_components: [...] } }

### Tool Implementations

| Tool | Cache Key | Cache TTL | Fallback |
| --- | --- | --- | --- |
| atomichub.getDNA | dna:effective:{uid}:{wid} | 30 min | GET /internal/mcp/dna |
| atomichub.listWorkspace | mcp:list:{uid}:{wid} | 5 min | GET /internal/mcp/list |
| atomichub.get | mcp:get:{repo_id}:{version} | 10 min | GET /internal/mcp/component |
| atomichub.search | mcp:search:{hash}:{uid} | 10 min | POST /internal/mcp/search (Qdrant) |
| atomichub.push | none (write operation) | — | POST /internal/mcp/push |
| atomichub.checkCoherence | none (compute on demand) | — | POST /internal/mcp/coherence |
| atomichub.diff | mcp:diff:{sha1}:{sha2} | 1 hr | GET /internal/mcp/diff |
| atomichub.getContracts | mcp:contracts:{wid} | 30 min | GET /internal/mcp/contracts |
| atomichub.suggestComposition | none | — | POST /internal/mcp/compose |

### Qdrant Setup for Semantic Search

// Qdrant Cloud collection setup (run once) await qdrant.createCollection('components_public', { vectors: { size: 1536, distance: 'Cosine' } // text-embedding-3-small dimensions }); await qdrant.createCollection('components_private', { vectors: { size: 1536, distance: 'Cosine' } }); // Index on component publish (BullMQ job: social:index) const embedding = await openai.embeddings.create({ model: 'text-embedding-3-small', input: `${component.name} ${component.description} ${propNames.join(' ')} ${codeSummary}` }); await qdrant.upsert('components_public', { points: [{ id: component.repo_id, vector: embedding.data[0].embedding, payload: { repo_id, user_id, framework, coherence_score, star_count } }] });

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T11-01 | Cloudflare Workers project setup (wrangler init, wrangler.toml) | Infra | None |
| T11-02 | Deploy MCP worker to CF Workers with custom domain mcp.atomichub.dev | Infra | T11-01 |
| T11-03 | Token validation in Worker: Redis lookup → internal API fallback | MCP | T11-01 |
| T11-04 | Internal API routes on Render: /internal/mcp/* (secured by shared secret) | Backend | None |
| T11-05 | Qdrant Cloud account + collection creation for public + private | Infra | None |
| T11-06 | OpenAI embedding pipeline: generate embedding on component publish | Backend | T11-05 |
| T11-07 | BullMQ job: social:index — embed + upsert to Qdrant on publish | Worker | T11-05, T11-06 |
| T11-08 | atomichub.getDNA tool implementation | MCP | T11-03, T11-04 |
| T11-09 | atomichub.listWorkspace tool implementation | MCP | T11-03, T11-04 |
| T11-10 | atomichub.get tool implementation with R2 presigned source fetch | MCP | T11-03, T11-04 |
| T11-11 | atomichub.search tool: Qdrant search + PostgreSQL hydration | MCP | T11-05, T11-04 |
| T11-12 | atomichub.push tool: create commit via internal API | MCP | T11-03, T11-04 |
| T11-13 | atomichub.checkCoherence tool | MCP | T11-03, T11-04 |
| T11-14 | atomichub.diff, atomichub.getContracts, atomichub.suggestComposition | MCP | T11-03, T11-04 |
| T11-15 | DNA context injection in every MCP response (_meta.dna_context) | MCP | T11-08 |
| T11-16 | MCP documentation page: how to add token to Claude Code config | Frontend | None |
| T11-17 | API token scopes UI: read-only vs read-write, workspace-scoped | Frontend | T06-06 |
| T11-18 | End-to-end MCP test: Claude Code fetches component, generates new one using DNA | Testing | T11-15 |

SPRINT 11 DONE WHEN Add ATOMICHUB_TOKEN to Claude Code config. Ask Claude to build a component. It calls atomichub.getDNA, atomichub.listWorkspace, atomichub.search, uses your DNA, and calls atomichub.push to save the result. All in one conversation.

SPRINT 12    Universal URL Import

| Duration 2 weeks | Goal Paste any URL → extracted + adapted + committed | Ship Import a ReactBits component in one command |
| --- | --- | --- |

### Import Pipeline

// Source extraction strategies (tried in order): // Strategy 1: Known domain parsers // reactbits.dev, magicui.design, ui.aceternity.com, ui.shadcn.com // Each has a parser that knows the page structure // Strategy 2: Generic <code> block extraction // Find largest <code> or <pre> block containing .tsx/.jsx // Strategy 3: GitHub raw URL detection // github.com/user/repo/blob/main/component.tsx → // raw.githubusercontent.com/user/repo/main/component.tsx // Strategy 4: CodeSandbox / StackBlitz embed URL // Fetch their file API directly // Strategy 5: Playwright headless fetch (last resort) // For JS-rendered pages that require JavaScript execution // SECURITY: Playwright runs in isolated container, blocks internal IPs

### Dependency Resolution

// After source extraction: function resolveDeps(source: string, projectPkgJson: PackageJson): DepManifest { // 1. Parse all import statements from source const imports = parseImports(source); // ts-morph // 2. Filter out relative imports and React (always present) const externalImports = imports.filter(i => !i.startsWith('.') && i !== 'react'); // 3. Check which are already in projectPkgJson.dependencies const existing = Object.keys(projectPkgJson.dependencies ?? {}); const missing = externalImports.filter(i => !existing.includes(i)); // 4. For each missing: verify it exists on npm (fetch registry.npmjs.org) // 5. Return: { peerDeps: string[], missing: string[], conflicts: ConflictInfo[] } return { peerDeps: externalImports, missing, conflicts: [] }; }

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T12-01 | POST /api/import — validate URL, quota check, enqueue import:fetch job | Backend | T10-04 |
| T12-02 | BullMQ queue: import:fetch + processor | Worker | T10-01 |
| T12-03 | SSRF protection: block private IP ranges + allowlist external domains | Backend | T12-01 |
| T12-04 | Known domain parsers: shadcn, reactbits, magicui, aceternity | Backend | T12-02 |
| T12-05 | Generic code block extractor: find largest TSX/JSX block in HTML | Backend | T12-02 |
| T12-06 | GitHub raw URL resolver: github.com → raw.githubusercontent.com | Backend | T12-02 |
| T12-07 | Playwright headless fetch: isolated container, internal IP blocked | Backend | T12-02 |
| T12-08 | Import statement parser: extract all imports from source (ts-morph) | Backend | T12-02 |
| T12-09 | npm registry checker: verify package exists + get version | Backend | T12-08 |
| T12-10 | Dep resolver: compute missing + conflicts against project package.json | Backend | T12-08 |
| T12-11 | Fork DNA adaptation: enqueue ai:generation job with type='adapt' | Backend | T12-02 |
| T12-12 | DNA adaptation processor: targeted color/spacing/font replacement | Worker | T07-14 |
| T12-13 | Post-adaptation coherence check + flag if <70 for review | Worker | T12-12 |
| T12-14 | POST /api/import/cli — CLI-facing import endpoint | Backend | T12-01 |
| T12-15 | CLI: atomichub import <url> command | CLI | T12-14 |
| T12-16 | Import UI: URL input field, progress states, dep manifest display | Frontend | T12-01 |
| T12-17 | Import result: show adapted component in Playground with diff from original | Frontend | T12-16 |
| T12-18 | 'Review adaptation' flow for low-coherence imports | Frontend | T12-13 |

SPRINT 12 DONE WHEN Paste a ReactBits component URL. AtomicHub fetches it, resolves its dependencies, adapts its colors and spacing to your DNA, and commits it to your library. atomichub import <url> does the same from terminal.

SPRINT 13    npm + Verdaccio

| Duration 2 weeks | Goal Self-hosted npm registry + auto-publish on tag | Ship npm install @username/atomichub-components works |
| --- | --- | --- |

### Verdaccio Deployment

# Render service: atomichub-registry # Docker image: verdaccio/verdaccio # Persistent disk: /verdaccio/storage (10GB, Render persistent disk) # config.yaml: storage: /verdaccio/storage auth: htpasswd: file: /verdaccio/htpasswd max_users: -1 uplinks: npmjs: { url: 'https://registry.npmjs.org/' } packages: '@*/atomichub-components': access: '$all' publish: '$authenticated' proxy: npmjs '**': access: '$all' proxy: npmjs # AtomicHub service account: atomichub-publish # Created via: htpasswd /verdaccio/htpasswd atomichub-publish # Stored as: VERDACCIO_TOKEN in Render env vars

### Auto-Publish Flow

// BullMQ job: vcs:publish (triggered on version tag creation) async function publishToVerdaccio(repoId: string, tag: string, userId: string) { // 1. Fetch source from R2 at commit SHA for this tag const source = await r2.get(commit.source_key); // 2. Fetch user's username const user = await db.query.users.findFirst({ where: eq(users.id, userId) }); // 3. Build package.json const pkgJson = { name: `@${user.username}/atomichub-components`, version: tag, main: './index.js', types: './index.d.ts', exports: { [`./${component.name}`]: `./${component.name}.tsx` }, peerDependencies: { react: '>=18.0.0', 'react-dom': '>=18.0.0' } }; // 4. Create tarball (tar + gzip) with package.json + source const tarball = await createTarball(pkgJson, source, component.name); // 5. PUT to Verdaccio registry API await verdaccioClient.publish(tarball, VERDACCIO_TOKEN); // 6. Update version_tags.npm_published = true await db.update(versionTags).set({ npm_published: true }).where(...); }

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T13-01 | Verdaccio Docker deployment on Render with persistent disk | Infra | None |
| T13-02 | Verdaccio config.yaml: scoped packages, proxy to npmjs | Infra | T13-01 |
| T13-03 | Create atomichub-publish service account in Verdaccio | Infra | T13-01 |
| T13-04 | BullMQ job: vcs:publish processor | Worker | T10-01, T05-01 |
| T13-05 | Tarball builder: package.json + source → .tgz | Backend | T13-04 |
| T13-06 | Verdaccio publish client: PUT tarball to registry API | Backend | T13-03, T13-04 |
| T13-07 | Trigger vcs:publish job on version tag creation (in S05 tag endpoint) | Backend | T13-04, T05-02 |
| T13-08 | Update version_tags.npm_published = true after publish | Backend | T13-06 |
| T13-09 | npm badge on releases page: show published status | Frontend | T13-08 |
| T13-10 | Install instructions on component page: npm + CLI variants | Frontend | T13-01 |
| T13-11 | Custom registry URL for users: registry.atomichub.dev | Infra | T13-01 |
| T13-12 | CLI: atomichub add uses our Verdaccio as registry source | CLI | T06-08 |
| T13-13 | Test end-to-end: tag component, verify npm install works from Verdaccio | Testing | T13-06 |

SPRINT 13 DONE WHEN Tag a component v1.0.0. It auto-publishes to Verdaccio. Run npm install @username/atomichub-components from any project and import the component. It works.

SPRINT 14    Cross-Project Sync

| Duration 2 weeks | Goal atomichub.lock + sync notifications + visual diff review + apply | Ship Fix a bug in Button, push to all projects |
| --- | --- | --- |

### DB Schema to Add

CREATE TABLE project_registrations ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), user_id UUID REFERENCES users(id) ON DELETE CASCADE, project_name TEXT NOT NULL, created_at TIMESTAMPTZ DEFAULT now() ); CREATE TABLE sync_subscriptions ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), project_id UUID REFERENCES project_registrations(id) ON DELETE CASCADE, repo_id UUID REFERENCES component_repos(id) ON DELETE CASCADE, current_tag TEXT NOT NULL, pinned_version TEXT, -- null = follow latest stable channel TEXT DEFAULT 'stable', UNIQUE(project_id, repo_id) ); CREATE TABLE sync_notifications ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), project_id UUID REFERENCES project_registrations(id) ON DELETE CASCADE, repo_id UUID REFERENCES component_repos(id), from_tag TEXT NOT NULL, to_tag TEXT NOT NULL, change_type TEXT NOT NULL, -- patch ¦ minor ¦ major status TEXT DEFAULT 'pending', created_at TIMESTAMPTZ DEFAULT now() );

### Sync Flow

// When component is tagged with new version: // BullMQ job: sync:notify async function notifySubscribers(repoId: string, fromTag: string, toTag: string) { const changeType = computeChangeType(fromTag, toTag); // patch¦minor¦major // Find all projects subscribed to this component const subs = await db.query.syncSubscriptions.findMany({ where: and( eq(syncSubscriptions.repo_id, repoId), isNull(syncSubscriptions.pinned_version) // skip pinned ) }); // Insert sync_notifications for each await db.insert(syncNotifications).values( subs.map(s => ({ project_id: s.project_id, repo_id: repoId, from_tag: fromTag, to_tag: toTag, change_type: changeType, status: 'pending' })) ); // patch → auto-approve (no user action needed) if (changeType === 'patch') { await autoApprovePatches(subs, repoId, toTag); } }

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T14-01 | DB migration: project_registrations, sync_subscriptions, sync_notifications | DB | T03-01 |
| T14-02 | POST /api/sync/register — register project (called by atomichub init) | Backend | T14-01 |
| T14-03 | POST /api/sync/subscribe — record which component version a project uses | Backend | T14-01 |
| T14-04 | GET /api/sync/status — pending notifications for all user projects | Backend | T14-01 |
| T14-05 | POST /api/sync/approve/:notifId — approve a sync | Backend | T14-01 |
| T14-06 | POST /api/sync/skip/:notifId — skip a sync | Backend | T14-01 |
| T14-07 | BullMQ job: sync:notify — fan-out notifications on tag creation | Worker | T14-01, T05-02 |
| T14-08 | Auto-approve patch versions: update current_tag, skip notification | Worker | T14-07 |
| T14-09 | CLI: atomichub sync — fetch approved updates, apply, update lock | CLI | T14-04 |
| T14-10 | CLI: atomichub sync --dry-run — preview without applying | CLI | T14-09 |
| T14-11 | CLI: atomichub pin <component> <version> — set pinned_version | CLI | T14-03 |
| T14-12 | CLI: atomichub status — show pending syncs with change types | CLI | T14-04 |
| T14-13 | Sync dashboard UI: pending notifications with visual diff links | Frontend | T14-04 |
| T14-14 | Dashboard badge: count of pending syncs (Redis: sync:pending:{uid}) | Frontend | T14-04 |
| T14-15 | Sync notification card: from/to version + change type + diff link + approve/skip | Frontend | T14-04 |
| T14-16 | Visual diff in sync review: compare from_tag vs to_tag (reuse S09 diff) | Frontend | T09-07 |

SPRINT 14 DONE WHEN Add a loading state to Button and tag it v1.1.0. Two registered projects get sync notifications. Review the visual diff, approve for Project A, skip for Project B. Run atomichub sync in Project A — Button source updates, lock file updates.

SPRINT 15    AI Suite Completion

| Duration 2 weeks | Goal A11y fixer + dark mode gen + responsive gen + composition suggester + video animation | Ship Full AI feature set live |
| --- | --- | --- |

### Feature Summary

| Feature | AI Model | Input | Output |
| --- | --- | --- | --- |
| Auto A11y Fixer | Claude claude-sonnet-4 | Component source + WCAG violations | Fixed source with PR opened automatically |
| Dark Mode Generator | Claude claude-sonnet-4 | Light mode component + dark palette from DNA | Dark mode variant (CSS vars or Tailwind dark:) |
| Responsive Generator | Claude claude-sonnet-4 | Desktop component + breakpoint config from DNA | Full responsive with sm:/md:/lg:/xl: classes |
| Composition Suggester | Claude haiku (fast) | User prompt + component library list from Qdrant | Composition code using existing components |
| Video → Animation | Gemini 1.5 Pro | MP4/GIF/WebM video | Framer Motion or CSS @keyframes component |

### A11y Fixer Flow

// POST /api/ai/a11y-fix { repo_id } // Worker: ai.a11y processor // 1. Fetch current source // 2. Run axe-core in headless browser (Playwright) → violation list // 3. Build prompt: 'Fix these WCAG violations: {violations}' // Include: source + violations + DNA (for color fix alternatives) // 4. Call Claude claude-sonnet-4 with fix prompt // 5. Diff: original vs fixed source // 6. Open PR on component repo: 'fix: auto-fix a11y violations' // 7. Show PR link to user

### Video → Animation Flow

// POST /api/ai/video { job_id } (video already uploaded to R2) // Worker: ai.video processor // 1. Fetch video from R2 // 2. Build Gemini prompt: 'Analyze this animation video. // Extract: element transforms, timing, easing curves. // Output: Framer Motion component with exact timing values.' // 3. Include DNA animation personality: preferred easing, duration range // 4. Call Gemini 1.5 Pro (user's Google AI key) // 5. Post-process: inject prefers-reduced-motion wrapper always // 6. Return generated Framer Motion component

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T15-01 | POST /api/ai/a11y-fix — endpoint + BullMQ job | Backend | T10-01 |
| T15-02 | axe-core Playwright integration: run a11y audit on rendered component | Worker | T09-03 |
| T15-03 | A11y fix processor: violations → Claude prompt → fixed source → PR | Worker | T15-02 |
| T15-04 | POST /api/ai/darkmode — endpoint + BullMQ job | Backend | T10-01 |
| T15-05 | Dark mode processor: extract colors → map to dark palette from DNA → rewrite | Worker | T07-14 |
| T15-06 | Dark mode contrast verification: check all color pairs for WCAG AA | Worker | T15-05 |
| T15-07 | POST /api/ai/responsive — endpoint + BullMQ job | Backend | T10-01 |
| T15-08 | Responsive processor: desktop component + DNA breakpoints → responsive classes | Worker | T07-14 |
| T15-09 | POST /api/ai/compose — endpoint (synchronous, fast via haiku) | Backend | None |
| T15-10 | Composition suggester: Qdrant search + haiku → composition code | Backend | T11-05 |
| T15-11 | POST /api/ai/video — endpoint + BullMQ job + video upload to R2 | Backend | T10-01 |
| T15-12 | Video processor: Gemini 1.5 Pro + motion extraction prompt | Worker | T15-11 |
| T15-13 | prefers-reduced-motion wrapper auto-injection | Worker | T15-12 |
| T15-14 | AI tools UI: section in component repo page + workspace page | Frontend | None |
| T15-15 | A11y fixer UI: trigger button + violation list + PR link on completion | Frontend | T15-01 |
| T15-16 | Dark mode generator UI: trigger button + before/after preview | Frontend | T15-04 |
| T15-17 | Responsive generator UI: trigger + breakpoint preview | Frontend | T15-07 |
| T15-18 | Video upload UI: drag-drop video + progress + result in Playground | Frontend | T15-11 |
| T15-19 | Composition suggester UI: prompt input in new-component flow | Frontend | T15-09 |
| T15-20 | Figma paste: read clipboard, detect Figma JSON, send to /api/ai/figma | Frontend | None |
| T15-21 | POST /api/ai/figma processor (Claude claude-sonnet-4 from Figma JSON) | Backend | T10-01 |

SPRINT 15 DONE WHEN All 5 AI features work end-to-end. Click 'Fix Accessibility' on any component and get a PR with fixes. Upload a video and get Framer Motion code. Generate dark mode and responsive variants in one click each.

SPRINT 16    Social Layer + Polish + Launch

| Duration 2 weeks | Goal Public feed + star + fork + comments + creator profiles + onboarding | Ship V1 SHIPS |
| --- | --- | --- |

FINAL SPRINT This sprint is 50% features (social layer) and 50% polish + launch preparation. The social layer makes AtomicHub feel alive — a place where developers share craft, not just store files. The polish work is what separates a portfolio project from a real product.

### Social Features

| Feature | What to Build | Priority |
| --- | --- | --- |
| Public Explore feed | Paginated feed of public components. Filters: framework, coherence threshold, human touch, DNA match, sort order. | Critical |
| Star | Star button on every component. star_count cached in Redis, persisted to DB. Starred components in user profile. | Critical |
| Fork | 'Fork to my library' button. Triggers DNA adaptation pipeline (S12 reuse). Upstream link maintained. | Critical |
| Comments | Threaded comments on component repo page. Reply support. Author avatars. | High |
| Creator profiles | Public /u/:username page. Auto-generated from published components. Shows DNA summary, star/fork stats. | High |
| Kit creation | Create named kit from subset of components. Public kits browsable in Explore. | Medium |
| Fork PR | 'Submit improvement to upstream' button on forked component. Opens PR to original author. | Medium |
| Trust badges | Human Crafted / AI Assisted / WCAG AA badges on every component card. | High |

### Onboarding Flow

- Step 1 (Auth): Sign up → Clerk

- Step 2 (DNA): 'Set up your design profile' — choice: 5-question wizard OR connect GitHub

- Step 3 (First component): 'Add your first component' — choice: paste code / upload screenshot / import URL

- Step 4 (CLI): 'Install the CLI' — shows npm install -g atomichub-cli + atomichub login

- Step 5 (MCP): 'Supercharge your AI' — shows how to add MCP token to Claude Code

- Dismiss: can skip any step, return from dashboard

### Launch Checklist

| Area | Item | Status |
| --- | --- | --- |
| Security | SSRF protection on URL import verified | Critical |
| Security | API key encryption (AES-256-GCM) in production | Critical |
| Security | Rate limiting on all AI endpoints (100/hr per user) | Critical |
| Security | Playwright network isolation for visual diff | Critical |
| Performance | Redis cache warming for top 100 public components | High |
| Performance | Qdrant index populated with seed components | High |
| Performance | Vercel Edge caching for public explore feed | High |
| UX | Empty states for all pages (no blank screens) | High |
| UX | Loading skeletons for all async operations | High |
| UX | Error boundaries with friendly messages | High |
| UX | Mobile responsive layout (web app) | Medium |
| Content | Seed library: publish 20+ quality components under @atomichub account | Critical |
| Content | Documentation: /docs — getting started, CLI reference, MCP setup | High |
| Content | Demo video: 3 min — signup → DNA setup → screenshot→component → MCP demo | Critical |
| Analytics | PostHog installed on web app + API events | Medium |
| Monitoring | Sentry configured on API + worker + MCP | High |

### Tasks

| ID | Task | Type | Deps |
| --- | --- | --- | --- |
| T16-01 | DB: stars, comments tables (already in schema from spec) | DB | T03-01 |
| T16-02 | POST/DELETE /api/components/:id/star — star/unstar | Backend | T16-01 |
| T16-03 | POST /api/components/:id/fork — fork + enqueue DNA adaptation | Backend | T12-11 |
| T16-04 | POST /api/components/:id/comments — create comment/reply | Backend | T16-01 |
| T16-05 | GET /api/explore — paginated public feed with all filters | Backend | T11-05 |
| T16-06 | GET /api/users/:username/profile — creator profile data | Backend | T02-08 |
| T16-07 | POST /api/kits — create kit from component selection | Backend | T16-01 |
| T16-08 | Star count Redis cache: INCR/DECR on star/unstar | Backend | T16-02 |
| T16-09 | Explore feed page: component cards with filters sidebar | Frontend | T16-05 |
| T16-10 | Component card: name, framework badge, coherence score, star count, trust badges | Frontend | T16-09 |
| T16-11 | Star button with optimistic update | Frontend | T16-02 |
| T16-12 | Fork button: trigger + progress indicator + link to new repo | Frontend | T16-03 |
| T16-13 | Comments section on component repo page | Frontend | T16-04 |
| T16-14 | Creator profile page /u/:username | Frontend | T16-06 |
| T16-15 | Kit creation UI: select components + name + publish | Frontend | T16-07 |
| T16-16 | Onboarding flow: 5-step wizard shown to new users | Frontend | T07-02 |
| T16-17 | Empty states: all major pages | Frontend | None |
| T16-18 | Loading skeletons: all async components | Frontend | None |
| T16-19 | Rate limiting middleware on AI endpoints | Backend | T10-04 |
| T16-20 | Security audit: SSRF, XSS, auth bypass, token exposure | Security | All |
| T16-21 | Seed content: publish 20+ components under @atomichub account | Content | S05 |
| T16-22 | Documentation pages: /docs/* with MDX | Frontend | None |
| T16-23 | PostHog analytics integration | Analytics | None |
| T16-24 | Sentry error tracking on all services | Monitoring | None |
| T16-25 | Demo video recording and embed on landing page | Content | All |

SPRINT 16 DONE WHEN AtomicHub is publicly accessible. New users can sign up, set up DNA, create a component, use the MCP, explore public components, fork one, and deploy. 20+ seed components in the public feed. Monitoring live.

# Sprint Dependency Map

Critical path: S01 → S02 → S03 → S04 → S05 → S06 → S10 → S11. Everything else branches from this spine. You cannot skip or reorder within the critical path.

S01 Foundation └── S02 Repo CRUD └── S03 Commit Engine ──────────────────────────────────────────┐ └── S04 Branching & PRs │ └── S05 Tags & Revert │ ├── S06 CLI ──────────────────────────────┐ │ │ └── (feeds into S10, S12, S14) │ │ ├── S07 DNA Engine ──────────────────┐ │ │ │ └── (feeds into S10, S11, S12) │ │ │ │ │ │ │ ├── S08 Prop Playground │ │ │ │ └── (feeds into S10, S09) │ │ │ │ │ │ │ ├── S09 Visual Diffing ◄───────────────┘ │ │ │ └── (feeds into S14, S16) │ │ │ │ │ └── S10 Screenshot→Component ◄──────────────┘ │ └── S11 MCP Server ◄──────────────────────┘ ├── (feeds into S15, S16) └── S12 URL Import └── S13 Verdaccio npm └── S14 Cross-Project Sync └── S15 AI Suite └── S16 Launch

# Risk Register

| Risk | Sprint | Severity | Mitigation |
| --- | --- | --- | --- |
| Playwright too slow for visual diff at scale | S09 | High | Cache screenshot diffs in R2 keyed by sha-pair. Only compute on first request per pair. Async computation — don't block PR creation. |
| Sandpack bundle size causes slow page loads | S08 | High | Lazy-load Sandpack. Show Monaco-only view first. Load Sandpack only when user opens Playground tab. |
| DNA analysis produces garbage for small codebases | S07 | High | Cold start wizard as mandatory fallback. Set confidence=40 for wizard-only DNA, show 'Improve DNA' prompt when confidence <60. |
| Claude vision misses DNA styling | S10 | High | Explicit constraint in prompt: 'ONLY use values from the design system below. No exceptions.' Add coherence check post-generation. Iteration loop for corrections. |
| Qdrant cold start — empty index for new users | S11 | Medium | Search own library first (always). Fall back to public Qdrant only when own library has <5 components. Show 'Add more components to improve search' tip. |
| Verdaccio storage fills up on Render | S13 | Medium | Set per-user package size quota. Verdaccio prunes old patch versions automatically (keep last 3). Alert at 80% disk usage. |
| GitHub OAuth scope rejected by users | S07 | Medium | Make GitHub analysis OPTIONAL — wizard is always available. Don't require GitHub scope. Prompt it as 'Improve your DNA' after wizard complete. |
| Playwright SSRF via visual diff URLs | S09 | Critical | Render all components from R2 source — never from user-provided URLs. Playwright has no network access except R2 CDN domain. |
| User API keys accidentally logged | S10 | Critical | Audit all log statements. Never log request bodies. API keys stored encrypted, decrypted only in worker memory. No key in error messages. |
| Conventional commit validation too strict | S03 | Low | Warn instead of blocking on non-conventional messages. Hard block only on empty messages. Add 'suggested format' tooltip. |

# Definition of Done — All Sprints

| Sprint | Demo Script (what you show at sprint review) |
| --- | --- |
| S01 | Open deployed Vercel URL, sign up with GitHub OAuth, show user row in Neon dashboard, hit /api/health and show {db: 'ok', redis: 'ok'}. |
| S02 | Create a workspace, create 3 component repos inside it with different frameworks, view them in grid, delete one. |
| S03 | Paste Button component code, commit it with 'feat: initial Button component', view it in Monaco, click the commit in history to see that exact source. |
| S04 | Create 'dark-mode' branch, commit a change on it, open PR against main, add inline comment, merge with squash. |
| S05 | Tag current Button as v1.0.0, show auto-generated release notes, view source at v1.0.0, click Revert and show the PR it creates. |
| S06 | Terminal demo: atomichub login (browser opens, returns to terminal), atomichub add Button (source appears in ./components/), atomichub push after editing. |
| S07 | Complete 5-question wizard, show DNA profile page with spacing/colors/typography/animation filled in. Connect GitHub, show DNA updated with real values. |
| S08 | Open Button in Playground, toggle variant prop (primary→ghost), see it change live, edit the code in Monaco and see preview update, change to mobile viewport. |
| S09 | Select v1.0.0 and v1.1.0, show all 4 diff types: code diff highlighted, prop diff table (new 'loading' prop), screenshot diff with draggable divider, score delta. |
| S10 | Upload a screenshot of a card component from any website, see AtomicHub generate matching React+Tailwind code with your DNA colors and spacing, iterate with 'make it more compact', commit it. |
| S11 | Add ATOMICHUB_TOKEN to Claude Code. Ask: 'Build me a profile card using my component library.' Show Claude calling getDNA, listWorkspace, search, get, checkCoherence, push — new ProfileCard in AtomicHub library. |
| S12 | Paste reactbits.dev component URL. Show AtomicHub fetch source, resolve deps, adapt to DNA, commit. Run atomichub import <url> in terminal, same result. |
| S13 | Tag Button v1.0.0, show Verdaccio dashboard, run npm install @username/atomichub-components in fresh project, import Button and render it. |
| S14 | Update Button with loading state, tag v1.1.0. Show 2 registered projects get sync notifications. Review visual diff (no loading vs with loading). Approve Project A. Run atomichub sync — source updates. |
| S15 | Click 'Fix Accessibility' on a component, show PR with WCAG fixes. Click 'Generate Dark Mode', show dark variant. Upload animation video, show Framer Motion output. Click 'Suggest Composition' — show existing components combined. |
| S16 | Complete new user sign-up flow → DNA wizard → upload screenshot → get component → add MCP to Claude Code → explore public feed → fork someone's component → kit created. System handles all this without errors. |

— END OF SPRINT PLAN —